Project title: Team-up: A Collaborative Study & Team Planning Hub

Team ID: 6

Team members: Malaika Farooq (1002311562), Aditi Vishal (1002387938), Amogh Dhole (1002055522), Krishan Lnu (1002306864)

Submission date: October 23, 2026

Sections 2 and 7 of the Project Progress Report. Repository: https://github.com/malaika-farooq/TeamUp_AdvSE-.git. Yellow-highlighted text is information only the team holds (dates, screenshots, defect log) and must be filled in or confirmed before submission.

2. Agile execution and backlog evidence

The team uses Scrum on a Jira Scrum board, as approved in the proposal (Section 4). This iteration added the in-repository evidence that links the board to the code: a documented Definition of Done, a sprint backlog with status and file-level evidence, backlog-ID conventions, pull-request and issue templates, and a CI workflow that enforces the automated parts of the Definition of Done (docs/agile/, CONTRIBUTING.md, .github/).

| Agile item | Current evidence |
| --- | --- |
| Method and cadence | Scrum with a Jira Scrum board (board screenshots: proposal Section 4.6). Two-week sprints; backlog PB-01 to PB-10 totalling 63 story points. Add actual start/end dates of Sprints 1-4. |
| Ceremonies actually performed | Planned per proposal: sprint planning at sprint start, 15-minute daily stand-up, weekly backlog refinement, sprint review and retrospective at sprint end. Retrospective outcomes are logged in docs/agile/README.md. Attach dates or screenshots for at least one planning, review and retrospective, and the stand-up record. |
| Definition of Done | Eight criteria from the proposal are written in docs/agile/DEFINITION_OF_DONE.md and copied into the pull-request template. Automated criteria (tests, type check, lint, build, accessibility) now run on every pull request through .github/workflows/ci.yml. Followed: yes for PB-01 to PB-07 and PB-10 on tests, build and deployment to the cloud environment. Not yet met: criterion 5 (permissions verified for different users) for PB-09, because the live database isolation tests have not been run. |
| Backlog management | Priorities (Must / Should) and estimates are unchanged from the proposal. 50 of 63 story points (79%) are done; PB-08 (AI matching, Should) and PB-09 (release hardening) are in progress. PB-08 stays the first item to defer if capacity runs out (risk R-01). Change found: the proposal plans four sprints but assigns PB-09 to Sprint 5 and PB-10 to Sprint 6; PB-10 is already done, and PB-09 must be completed inside the remaining time. See Section 8. |
| Repository / issue tracking | From this iteration, every branch, commit and pull request carries a backlog ID (for example feature/PB-04-..., commit message "PB-03: ..."), documented in CONTRIBUTING.md. Issue templates (user story, bug with Critical/Major/Minor severity) and a pull-request template with the Definition of Done checklist are in .github/. docs/agile/SPRINT_BACKLOG.md maps each PB item to the files and tests that implement it. Earlier commits were not retro-tagged. |

2.1 Sprint / iteration progress

| ID | User story / task | Planned sprint | Estimate (SP) | Status | Evidence / link |
| --- | --- | --- | --- | --- | --- |
| PB-01 | Register, sign in, manage profile (courses, skills, availability) | Sprint 1 | 8 | Done | routes/auth.tsx, onboarding.tsx, settings.tsx; auth and auth-middleware unit tests |
| PB-02 | Create team, invite, request to join, owner approves | Sprint 1 | 8 | Done | teams.index.tsx, teams.$teamId.tsx, discover.tsx, invite.$token.tsx |
| PB-03 | Shared calendar with availability-based meeting times | Sprint 2 | 8 | Done | SessionsPanel.tsx, sessions/schedule.ts; schedule.test.mjs (19 tests added this iteration) |
| PB-04 | Tasks with owners, due dates, status on a shared board | Sprint 2 | 5 | Done | TaskBoard.tsx, tasks/errors.ts; queries.test.mjs |
| PB-05 | Shared notes, links and file references | Sprint 3 | 5 | Done | ResourcesPanel.tsx; storage policies migration 0001 |
| PB-06 | In-app notifications | Sprint 3 | 5 | Done | notifications/api/queries.ts, AppShell.tsx |
| PB-07 | Progress dashboard | Sprint 4 | 8 | Done | dashboard.tsx, activity/api/queries.ts |
| PB-08 | AI teammate / session suggestions | Sprint 4 | 8 | In progress | backend/ai/ai.functions.ts, assistant.tsx; ai-gateway and ai-handlers tests. Pending: 20-sample relevance review |
| PB-09 | Release workflows with verified permissions and clear errors | Sprint 5 | 5 | In progress | Accessibility suite (22 checks), error handling in task and session flows. Pending: live permission tests |
| PB-10 | Filter tasks by owner, due date, status | Sprint 6 | 3 | Done | FilterSelect in TaskBoard.tsx |

Totals: 63 SP planned; 50 SP done (79%); 13 SP in progress (21%). Add per-sprint velocity from Jira (SP completed in each sprint).

7. Testing, quality, and updated risk status

All results below were produced by running the commands on the repository with Node 24 on October 23, 2026 (details: docs/testing/TEST_REPORT.md). Coverage is measured over the modules the unit suite loads (backend handlers, authentication, queries, shared libraries, scheduling logic); it is not whole-application coverage.

| Area | What has been tested | Tool / method | Current result | Target / pass criterion | Next action |
| --- | --- | --- | --- | --- | --- |
| Functional | Authentication and token handling; team, task, session, resource, notification, activity and profile queries (scoping, errors, payloads); AI handlers; sample workspace; weekly recurrence and availability-overlap calculation; task permission messages | Unit tests with Node's built-in test runner; Supabase boundary mocked | 160 / 160 passed (141 existing + 19 added). Line coverage 99.79%, branches 95.70% | >= 90% pass rate; >= 70% line coverage on core logic. Met | Run and record the manual system flow (create team, invite, assign task, mark complete) from tests/manual/. Add results. |
| Automated | Component accessibility and keyboard behaviour on the production components | Playwright + axe-core, desktop and mobile Chromium | 22 / 22 passed. Type check, lint (0 errors, 13 warnings) and production build also pass | 100% of critical-flow tests pass before final submission. Pending | Cypress end-to-end tests for FR-01, FR-02, FR-04 are not written yet. Either write them or get approval to use Playwright, which is already in the repository. |
| Nonfunctional | Security: token verification, cron secret rotation. Accessibility: WCAG 2 A/AA and 2.1 A/AA, light and dark, keyboard, focus trap, reflow. Performance and uptime: not tested | Unit tests; axe-core; k6 planned for NFR-01 | Security and accessibility checks pass. NFR-01 (95% of loads under 2 s with 50 users) and NFR-04 (99% uptime) not measured | NFR-01 as stated; NFR-03 spot check on key pages | Write the k6 script for task board and dashboard; run the screen-reader spot check; collect uptime and error logs. |
| AI feature | Membership check before any provider call, scoping of team data, candidate filtering, provider errors, rate limits, malformed or fenced JSON output | Unit tests on handlers and gateway; human review planned | Handler and gateway tests pass. 0 of 20 sample suggestions reviewed by a human | Review >= 20 sample suggestions for relevance and acceptance rate | Review 20 suggestions from representative student profiles and record relevance and acceptance. |

Not yet run: the six live database isolation (row-level security) tests, because they need a dedicated Supabase test project with two test users; and the manual browser and permission scenarios. A skipped or unwritten test is not counted as passing. Confirm from Jira that no Critical defect is open.

7.1 Risk update

| ID | Risk statement | P | I | P×I | Status / trigger | Response, owner, and action taken |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Because the project combines many features within 8 weeks, capacity may run out, resulting in incomplete mandatory features or late delivery. | 3 | 4 | 12 | Reduced (was 16) | Every Must story except PB-09 is done (50 of 63 SP). Remaining: AI evaluation, PB-09, end-to-end and load tests. Defer PB-08 first if needed. Owner: project lead. |
| R-02 | Because members build connected modules separately, incompatible APIs or schema changes may cause integration failures, resulting in rework. | 2 | 4 | 8 | Reduced (was 12) | Shared generated database types, versioned migrations, type check, 160 unit tests, and CI on every pull request. Owner: technical lead. |
| R-03 | Because the system stores profiles and private team content, incorrect access rules may expose data to unauthorized users, resulting in privacy breach. | 3 | 5 | 15 | Open, unchanged | Server-side membership checks and row-level security are in place and unit-tested, but live isolation tests have not run, so exposure is not reduced. Next: run the integration suite on a test project. Owner: backend/security lead. |
| R-04 | Because students have different schedules, members may be unavailable, resulting in delayed tasks and uneven workload. | 4 | 3 | 12 | Open | Backup owners on critical tasks, redistribution at stand-up, board visibility in Jira. Owner: Scrum Master. |
| R-05 | Because AI matching depends on an external service and can be inaccurate or biased, the feature may fail or give poor matches. | 3 | 3 | 9 | Open | Membership is checked before provider calls; failures and malformed output fall back safely (tested); manual team search remains. Pending: 20-sample review. Owner: AI integration lead. |
| R-06 (new) | Because the Cypress end-to-end and k6 load tests promised in the proposal have not been run, defects in critical flows or slow pages may reach submission, resulting in failed quality criteria. | 3 | 4 | 12 | New | Write the three Cypress flows (FR-01, FR-02, FR-04) and a 50-user k6 script next sprint. Owners: Amogh Dhole, Krishan Lnu. |

Probability and impact changes for R-01 and R-02 are proposed from the evidence above; the team confirms them.